## Summary
CM Workorders Compliance from April-2025 to March-2026
S.No | Month | Total Work Orders | Completed | Pending to be Executed / Trial run pending after job completion / In-progress
1 | 2025-04-01 | 59 | 34 | 25
2 | 2025-05-01
3 | 2025-06-01
4 | 2025-07-01
5 | 2025-08-01
6 | 2025-09-01
7 | 2025-10-01
8 | 2025-11-01
9 | 2025-12-01
10 | 2026-01-01
11 | 2026-02-01
12 | 2026-03-01
Total |  | 59 | 34 | 25
Total compliance for FY 25-26 (% ) |  |  |  | 57.6271

## Apr-25
Status | Order | Description | Order Type | MaintActivType | Priority | Bas. start date | System status | User status | Functional Loc. | Notification | Planning Plant | Planner Group | PriorityType | Priority | MaintPlant | Plant | Plant Section | PGrp Task List | Equipment | Created On | Entered By | Resp. cost cntr
Pending | 170000005047 | 008P106A: Improve base rigidity | PM07 | CMC | 3 | 2025-04-01 | REL NMAT PRC SETC |  | HP-REF-6600-PNUT-V042-008PM106A | 400000006386 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006328 | 2025-04-01 | 31993840 | 6600RY01
Pending | 170000005053 | 4EM60B: Fan bearings replacement | PM07 | CMC | 3 | 2025-04-01 | REL NMAT PRC SETC |  | HP-REF-6600-FCCU-V010-004EM060B | 400000006445 | 6600 | R01 | PM | Low | V010 | 6600 | 004 |  | 15004602 | 2025-04-01 | 31993840 | 6600RY01
Pending | 170000005056 | 46PM14B: Motor brgs replacement | PM07 | CMC | 3 | 2025-04-01 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-CRDU-V003-046PM014B | 400000006448 | 6600 | R01 | PM | Low | V003 | 6600 | 046 |  | 12011771 | 2025-04-01 | 31993840 | 6600RY01
Pending | 170000005057 | 4KM8102B: Fan impeller balancing | PM07 | CMC | 3 | 2025-04-01 | REL NMAT PRC SETC |  | HP-REF-6600-FCCU-V010-004KM102B | 400000006449 | 6600 | R01 | PM | Low | V010 | 6600 | 004 |  | 15004618 | 2025-04-01 | 31993840 | 6600RY01
Completed | 170000005045 | 42PM21A: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-01 | WCM WOCO REL CNF CSER GMPS JBFI MANC* | JCOM | HP-REF-6600-CRDU-V003-042PM021A | 400000006443 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011672 | 2025-04-01 | 31993840 | 6600RY01
Completed | 170000005046 | 75AM1C: Adjust belt tension | PM07 | CMC | 3 | 2025-04-01 | TECO CNF JBFI NMAT PRC SETC | JCOM | HP-REF-6600-MSBL-V020-075AM001C | 400000006385 | 6600 | R01 | PM | Low | V020 | 6600 | 075 |  | 15005046 | 2025-04-01 | 31993840 | 6600RY01
Completed | 170000005054 | 4PM8102B: Motor brgs replacement | PM07 | CMC | 3 | 2025-04-01 | WCM WOCO REL CNF CSER GMPS JBFI MANC* | JCOM | HP-REF-6600-FCCU-V010-004PM8102B | 400000006446 | 6600 | R01 | PM | Low | V010 | 6600 | 004 |  | 12011931 | 2025-04-01 | 31993840 | 6600RY01
Completed | 170000005055 | 15PM55B: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-01 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-FCCU-V011-015PM055B | 400000006447 | 6600 | R01 | PM | Low | V011 | 6600 | 015 |  | 12012027 | 2025-04-01 | 31993840 | 6600RY01
Completed | 170000005062 | 8PM104B: Alignment checking & correction | PM07 | CMC | 3 | 2025-04-02 | REL NMAT PRC SETC |  | HP-REF-6600-PNUT-V042-008PM104B | 400000006326 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006325 | 2025-04-02 | 31993840 | 6600RY01
Completed | 170000005063 | 90PM3A: Motor soft-foot correction | PM07 | CMC | 3 | 2025-04-02 | WCM EXEC REL NMAT PRC SETC |  | HP-REF-6600-DISL-V032-090PM003A | 400000006392 | 6600 | R01 | PM | Low | V032 | 6600 | 090 |  | 12012810 | 2025-04-02 | 31993840 | 6600RY01
Pending | 170000005071 | 90PG101F: Pump bearings replacement | PM07 | CMC | 3 | 2025-04-03 | REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-VOFS-V124-PG101F | 400000006403 | 6600 | R02 | PM | Low | V124 | 6600 |  |  | 15007763 | 2025-04-03 | 31993840 | 6600RY02
Completed | 170000005069 | 4PM67A: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-03 | WCM WOCO REL CNF CSER GMPS JBFI MANC* | JCOM | HP-REF-6600-FCCU-V010-004PM067A | 400000006421 | 6600 | R01 | PM | Low | V010 | 6600 | 004 |  | 12011877 | 2025-04-03 | 31993840 | 6600RY01
Completed | 170000005070 | 072AM003B2: Belt tension adjustment | PM07 | CMC | 3 | 2025-04-03 | WCM EXEC REL CSER GMPS MACM PRC SETC | JCOM | HP-REF-6600-MSBL-V021-072AM003B2 | 400000006402 | 6600 | R01 | PM | Low | V021 | 6600 | 072 |  | 15005160 | 2025-04-03 | 31993840 | 6600RY01
Pending | 170000005076 | 616KM102C: Blower bearings replacement | PM07 | CMC | 3 | 2025-04-04 | CRTD NMAT PRC |  | HP-REF-6600-VETP-V123-616KM102C | 400000006327 | 6600 | R02 | PM | Low | V123 | 6600 | 616 |  | 15007447 | 2025-04-04 | 31993840 | 6600RY02
Pending | 170000005082 | 24PM010A: Spider repl and alignment. | PM07 | CMC | 3 | 2025-04-07 | WCM EXEC REL NMAT PRC SETC |  | HP-REF-6600-PNUT-V040-024PM010A | 400000006439 | 6600 | R01 | PM | Low | V040 | 6600 | 024 |  | 15005870 | 2025-04-05 | 31996010 | 6600RY01
Pending | 170000005089 | 507PM2102A: Pump internals inspection | PM07 | CMC | 3 | 2025-04-07 | REL NMAT PRC SETC |  | HP-REF-6600-VSRU-V107-507PM2102A | 400000006379 | 6600 | R02 | PM | Low | V107 | 6600 | 507 |  | 15006897 | 2025-04-07 | 31993840 | 6600RY02
Pending | 170000005091 | 42EM30E: Fan bearings replacement | PM07 | CMC | 3 | 2025-04-07 | REL NMAT PRC SETC |  | HP-REF-6600-CRDU-V003-042EM030E | 400000006501 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 15003666 | 2025-04-07 | 31993840 | 6600RY01
Completed | 170000005090 | 42PM6B: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-07 | REL CNF JBFI MANC NMAT PRC SETC | JCOM | HP-REF-6600-CRDU-V003-042PM006B | 400000006500 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011636 | 2025-04-07 | 31993840 | 6600RY01
Completed | 170000005092 | 42EM30H: Fan belt replacement | PM07 | CMC | 3 | 2025-04-07 | REL CNF JBFI NMAT PRC SETC | JCOM | HP-REF-6600-CRDU-V003-042EM030H | 400000006502 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 15003669 | 2025-04-07 | 31993840 | 6600RY01
Completed | 170000005093 | 42EM30I: Motor NLT & Fan PM Check | PM07 | CMC | 3 | 2025-04-07 | REL NMAT PRC SETC |  | HP-REF-6600-CRDU-V003-042EM030I | 400000006503 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 15003670 | 2025-04-07 | 31993840 | 6600RY01
Completed | 170000005094 | 120PM21B: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-07 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-OMNS-V022-120PM021B | 400000006491 | 6600 | R01 | PM | Low | V022 | 6600 | 120 |  | 12013072 | 2025-04-07 | 31993840 | 6600RY01
Completed | 170000005100 | 190XM004C: Blower bearing replacement. | PM07 | CMC | 3 | 2025-04-08 | WCM REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-ETPS-V062-190XM004 | 400000006492 | 6600 | R01 | PM | Low | V062 | 6600 | 190 |  | 15004586 | 2025-04-08 | 31993840 | 6600RY01
Pending | 170000005101 | 502AM103B2: Check motor pulley and belt | PM07 | CMC | 3 | 2025-04-09 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-VNIU-V102-502AM103B | 400000006462 | 6600 | R02 | PM | Low | V102 | 6600 | 502 |  | 12022312 | 2025-04-09 | 31993840 | 6600RY02
Pending | 170000005102 | 502AM102H2: Check motor pulley and belt | PM07 | CMC | 3 | 2025-04-09 | CRTD NMAT PRC |  | HP-REF-6600-VNIU-V102-502AM102H2 | 400000006463 | 6600 | R02 | PM | Low | V102 | 6600 | 502 |  | 12022308 | 2025-04-09 | 31993840 | 6600RY02
Pending | 170000005108 | 008KM105G: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-09 | REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-PNUT-V042-008KM105G | 400000006288 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 12013607 | 2025-04-09 | 31993840 | 6600RY01
Pending | 170000005109 | 505PM2711B: Replace Pump NDE bearing | PM07 | CMC | 3 | 2025-04-09 | CRTD NMAT PRC |  | HP-REF-6600-VHGU-V105-505PM2711B | 400000006493 | 6600 | R02 | PM | Low | V105 | 6600 | 505 |  | 15007153 | 2025-04-09 | 31993840 | 6600RY02
Completed | 170000005106 | 171M101F: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-09 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-PNUT-V040-171PM101F | 400000006286 | 6600 | R01 | PM | Low | V040 | 6600 | 171 |  | 12013264 | 2025-04-09 | 31993840 | 6600RY01
Completed | 170000005107 | 171PM101F: Pump bearings Repalcement | PM07 | CMC | 3 | 2025-04-09 | REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-PNUT-V040-171PM101F | 400000006287 | 6600 | R01 | PM | Low | V040 | 6600 | 171 |  | 15005847 | 2025-04-09 | 31993840 | 6600RY01
Completed | 170000005110 | 505PM2701B: Inspect Pump NDE bearing | PM07 | CMC | 3 | 2025-04-09 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-VHGU-V105-505PM2701B | 400000006494 | 6600 | R02 | PM | Low | V105 | 6600 | 505 |  | 15007151 | 2025-04-09 | 31993840 | 6600RY02
Completed | 170000005114 | 028PM011A: Replace motor bearings, Check | PM07 | CMC | 3 | 2025-04-11 | CRTD NMAT PRC |  | HP-REF-6600-ETPS-V060-028PM011A | 400000006406 | 6600 | R01 | PM | Low | V060 | 6600 | 028 |  | 12013961 | 2025-04-10 | 31996010 | 6600RY01
Pending | 170000005122 | 606PM1702: Replace Pump Bearings | PM07 | CMC | 3 | 2025-04-11 | CRTD NMAT PRC | WMAT | HP-REF-6600-VCPP-V117 | 400000006521 | 6600 | R02 | PM | Low | 6600 | 6600 |  |  |  | 2025-04-11 | 32001730 | 6600RY02
Completed | 170000005120 | 072AM003D1: Replace Motor bearings | PM07 | CMC | 3 | 2025-04-11 | REL CSER GMPS MACM PRC SETC | JCOM | HP-REF-6600-MSBL-V021-072AM003D1 | 400000006454 | 6600 | R01 | PM | Low | V021 | 6600 | 072 |  | 12012258 | 2025-04-11 | 31993840 | 6600RY01
Completed | 170000005121 | 008PM104B: Soft foot & alignment correct | PM07 | CMC | 3 | 2025-04-11 | WCM EXEC REL NMAT PRC SETC |  | HP-REF-6600-PNUT-V042-008PM104B | 400000006520 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006325 | 2025-04-11 | 32001730 | 6600RY01
Pending | 170000005128 | 606PM1702: Replace motor bearings | PM07 | CMC | 3 | 2025-04-15 | REL NMAT PRC SETC |  | HP-REF-6600-VCPP-V117 | 400000006497 | 6600 | R02 | PM | Low | 6600 | 6600 |  |  |  | 2025-04-12 | 32001730 | 6600RY02
Pending | 170000005130 | 130PM020A: Replace Motor bearings | PM07 | CMC | 3 | 2025-04-15 | CRTD NMAT PRC | WMAT | HP-REF-6600-PNUT-V040-130PM020A | 400000006504 | 6600 | R01 | PM | Low | V040 | 6600 | 130 |  | 12013343 | 2025-04-12 | 32001730 | 6600RY01
Completed | 170000005126 | 701PM109B: Replace Motor bearings | PM07 | CMC | 3 | 2025-04-15 | REL NMAT PRC SETC |  | HP-REF-6600-VOFS-V124-701PM109B | 400000006495 | 6600 | R02 | PM | Low | V124 | 6600 |  |  | 12024287 | 2025-04-12 | 32001730 | 6600RY02
Completed | 170000005127 | 606PM1703: Replace motor bearings | PM07 | CMC | 3 | 2025-04-15 | REL NMAT PRC SETC |  | HP-REF-6600-VCPP-V117 | 400000006496 | 6600 | R02 | PM | Low | 6600 | 6600 |  |  |  | 2025-04-12 | 32001730 | 6600RY02
Pending | 170000005145 | 42PM18C: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-15 | CRTD MACM PRC | WMAT | HP-REF-6600-CRDU-V003-042PM018C | 400000006474 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011667 | 2025-04-15 | 31993840 | 6600RY01
Completed | 170000005138 | 42PM8B: Coupling shims replacement | PM07 | CMC | 3 | 2025-04-15 | WCM WOCO REL CNF CSER GMPS JBFI MANC* | JCOM | HP-REF-6600-CRDU-V003-042PM008B | 400000006467 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 15003709 | 2025-04-15 | 31993840 | 6600RY01
Completed | 170000005148 | 171PM101D: Pump DE bearing replacement | PM07 | CMC | 3 | 2025-04-16 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-PNUT-V040-171PM101D | 400000006468 | 6600 | R01 | PM | Low | V040 | 6600 | 171 |  | 15005845 | 2025-04-16 | 31993840 | 6600RY01
Completed | 170000005150 | 92PM9B: Replace Pump bearings | PM07 | CMC | 3 | 2025-04-16 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-SRUS-V033-092PM009B | 400000006457 | 6600 | R01 | PM | Low | V033 | 6600 | 092 |  | 15006563 | 2025-04-16 | 31993840 | 6600RY01
Completed | 170000005151 | 609P101A:Coupling inspection & alignment | PM07 | CMC | 3 | 2025-04-16 | CRTD NMAT PRC |  | HP-REF-6600-VCNU-V120-609PM101A | 400000006458 | 6600 | R02 | PM | Low | V120 | 6600 | 609 |  | 15003357 | 2025-04-16 | 31993840 | 6600RY02
Completed | 170000005162 | 72AM3C2: Fan belt replacement | PM07 | CMC | 3 | 2025-04-16 | WCM EXEC REL CNF CSER GMPS JBFI MANC* | JCOM | HP-REF-6600-MSBL-V021-072AM003C2 | 400000006552 | 6600 | R01 | PM | Low | V021 | 6600 | 072 |  | 15005162 | 2025-04-17 | 31993840 | 6600RY01
Completed | 170000005172 | 505PM2701A: Inspect pump NDE bearing. | PM07 | CMC | 3 | 2025-04-21 | WCM EXEC CRTD NMAT PRC |  | HP-REF-6600-VHGU-V105-505PM2701A | 400000006507 | 6600 | R02 | PM | Low | V105 | 6600 | 505 |  | 15007150 | 2025-04-19 | 31993840 | 6600RY02
Pending | 170000005187 | 703LZ1BK2A: Blower belts replacement | PM07 | CMC | 3 | 2025-04-22 | CRTD NMAT PRC | WMAT | HP-REF-6600-VSSH-V125-703LZ0001BK02A | 400000006583 | 6600 | R02 | PM | Low | V125 | 6600 | 703 |  | 15006989 | 2025-04-22 | 31993840 | 6600RY02
Pending | 170000005188 | 170PM7A: Replace Pump DE & NDE bearings | PM07 | CMC | 3 | 2025-04-22 | REL NMAT PRC SETC |  | HP-REF-6600-PNUT-V041-170PM007A | 400000006584 | 6600 | R01 | PM | Low | V041 | 6600 | 170 |  | 15006079 | 2025-04-22 | 31993840 | 6600RY01
Pending | 170000005189 | 85PM2002: Offer Motor No-load trial | PM07 | CMC | 3 | 2025-04-22 | REL NMAT PRC SETC |  | HP-REF-6600-ETPS-V061-085PM2002 | 400000006585 | 6600 | R01 | PM | Low | V061 | 6600 | 085 |  | 12014160 | 2025-04-22 | 31993840 | 6600RY01
Completed | 170000005190 | 701PM105A: Motor insitu balancing | PM07 | CMC | 3 | 2025-04-22 | REL NMAT PRC SETC |  | HP-REF-6600-VOFS-V124-701PM105A | 400000006508 | 6600 | R01 | PM | Low | V124 | 6600 |  |  | 12024277 | 2025-04-22 | 31993840 | 6600RY01
Completed | 170000005191 | 614KM201B: Replace Compressor bearings | PM07 | CMC | 3 | 2025-04-22 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-MERX-V054-ROTARYEQPT | 400000006509 | 6600 | R01 | PM | Low | V054 | 6600 | 281 |  |  | 2025-04-22 | 31993840 | 6600RY01
Pending | 170000005199 | 75PM51A: Replace Motor brgs | PM07 | CMC | 3 | 2025-04-24 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-MSBL-V020-075PM051A | 400000006558 | 6600 | R01 | PM | Low | V020 | 6600 | 075 |  | 12012181 | 2025-04-24 | 31993840 | 6600RY01
Pending | 170000005200 | 72PM05B: Pump bearings replacement | PM07 | CMC | 3 | 2025-04-24 | CRTD NMAT PRC | WMAT | HP-REF-6600-MSBL-V021-072PM005B | 400000006559 | 6600 | R01 | PM | Low | V021 | 6600 | 072 |  | 15005180 | 2025-04-24 | 31993840 | 6600RY01
Pending | 170000005201 | 72PM04A: Pump bearings replacement | PM07 | CMC | 3 | 2025-04-24 | CRTD NMAT PRC | WMAT | HP-REF-6600-MSBL-V021-072PM004A | 400000006600 | 6600 | R01 | PM | Low | V021 | 6600 | 072 |  | 15005177 | 2025-04-24 | 31993840 | 6600RY01
Pending | 170000005203 | 74-K-2B: Cyl#2 & Cyl#4 Internals inspect | PM07 | CMC | 3 | 2025-04-25 | WCM CRTD NMAT PRC |  | HP-REF-6600-MSBL-V021-074KM002B | 400000006529 | 6600 | R01 | PM | Low | V021 | 6600 | 074 |  | 15005214 | 2025-04-25 | 31993840 | 6600RY01
Completed | 170000005204 | 42M15B: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-25 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-CRDU-V003-042PM015B | 400000006592 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011660 | 2025-04-25 | 31993840 | 6600RY01
Completed | 170000005206 | 015M002E: Motor Bearing Replacement | PM07 | CMC | 3 | 2025-04-25 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-FCCU-V011-015PM002E | 400000006620 | 6600 | R01 | PM | Low | V011 | 6600 | 015 |  | 12012008 | 2025-04-25 | 31993840 | 6600RY01
Completed | 170000005218 | 42PM18B: Motor bearings replacement | PM07 | CMC | 3 | 2025-04-28 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-CRDU-V003-042PM018B | 400000006587 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011666 | 2025-04-28 | 31993840 | 6600RY01
Completed | 170000005220 | 505PM1101A: Inspect PNDE bearing | PM07 | CMC | 3 | 2025-04-28 | CRTD NMAT PRC |  | HP-REF-6600-VHGU-V105-505PM1101A | 400000006602 | 6600 | R02 | PM | Low | V105 | 6600 | 505 |  | 15007132 | 2025-04-28 | 31993840 | 6600RY02
Pending | 170000005227 | 701PM105A: Motor bearings inspection | PM07 | CMC | 3 | 2025-04-30 | CRTD NMAT PRC |  | HP-REF-6600-OFFS-V038-ROTARYEQPT | 400000006549 | 6600 | R02 | PM | Low | V038 | 6600 | 120 |  |  | 2025-04-30 | 31993840 | 6600RY02
Completed | 170000005226 | 92PM16A: Coupling shims replacement | PM07 | CMC | 3 | 2025-04-30 | WCM EXEC REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-SRUS-V033-092PM016A | 400000006548 | 6600 | R01 | PM | Low | V033 | 6600 | 092 |  | 15006570 | 2025-04-30 | 31993840 | 6600RY01

## May-25
| Order | Description | Order Type | MaintActivType | Priority | Bas. start date | System status | User status | Functional Loc. | Notification | Planning Plant | Planner Group | PriorityType | Priority | MaintPlant | Plant | Plant Section | PGrp Task List | Equipment | Created On | Entered By | Resp. cost cntr
Pending | 170000005234 | 11PM4B: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-02 | WCM REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-CRDU-V002-011PM004B | 400000006564 | 6600 | R01 | PM | Low | V002 | 6600 | 011 |  | 12011497 | 2025-05-02 | 31993840 | 6600RY01
Pending | 170000005236 | 170PM8A: Pump bearings replacement | PM07 | CMC | 3 | 2025-05-05 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V041-170PM008A | 400000006588 | 6600 | R01 | PM | Low | V041 | 6600 | 170 |  | 15006082 | 2025-05-03 | 31993840 | 6600RY01
Pending | 170000005237 | 170PM8B:Pump bearings replacement | PM07 | CMC | 3 | 2025-05-05 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V041-170PM008B | 400000006589 | 6600 | R01 | PM | Low | V041 | 6600 | 170 |  | 15006083 | 2025-05-03 | 31993840 | 6600RY01
Pending | 170000005238 | 120P007A: Pump internals inspection | PM07 | CMC | 3 | 2025-05-05 | CRTD NMAT PRC |  | HP-REF-6600-OMNS-V022-120PM007D | 400000006645 | 6600 | R01 | PM | Low | V022 | 6600 | 120 |  | 15005611 | 2025-05-03 | 31993840 | 6600RY01
Pending | 170000005240 | 503AM104B: Fan belt replacement | PM07 | CMC | 3 | 2025-05-05 | WCM EXEC CRTD NMAT PRC |  | HP-REF-6600-VHCU-V103-503A104B | 400000006646 | 6600 | R02 | PM | Low | V103 | 6600 | 503 |  |  | 2025-05-03 | 31993840 | 6600RY02
Completed | 170000005241 | 505K1901PM04: Motor soft-foot correction | PM07 | CMC | 3 | 2025-05-05 | CRTD NMAT PRC | JCOM | HP-REF-6600-VHGU-V105-505KM1901 | 400000006647 | 6600 | R02 | PM | Low | V105 | 6600 | 505 |  | 12020622 | 2025-05-03 | 31993840 | 6600RY02
Completed | 170000005250 | 11PT2B: Pump NDE bearing replacement | PM07 | CMC | 3 | 2025-05-05 | REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-CRDU-V002-011PT002B | 400000006615 | 6600 | R01 | PM | Low | V002 | 6600 | 011 |  | 15003601 | 2025-05-05 | 31993840 | 6600RY01
Completed | 170000005253 | 7PM2A: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-05 | WCM REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-MERX-V052-007PM002A | 400000006660 | 6600 | R01 | PM | Low | V052 | 6600 | 007 |  | 12013917 | 2025-05-05 | 31993840 | 6600RY01
Completed | 170000005254 | 511PM5B: Soft-foot & alignment check | PM07 | CMC | 3 | 2025-05-05 | WCM EXEC CRTD NMAT PRC |  | HP-REF-6600-VSRU-V107-ROTARY_EQUIPMENT | 400000006661 | 6600 | R02 | PM | Low | V107 | 6600 | 507 |  |  | 2025-05-05 | 31993840 | 6600RY02
Pending | 170000005255 | 616KM102B: Inspect/Replace Blower brgs | PM07 | CMC | 3 | 2025-05-05 | CRTD NMAT PRC |  | HP-REF-6600-VETP-V123-616KM102B | 400000006662 | 6600 | R02 | PM | Low | V123 | 6600 | 616 |  | 15007446 | 2025-05-05 | 31993840 | 6600RY02
Pending | 170000005256 | 616KM102D: Inspect/Free up Blower rotor | PM07 | CMC | 3 | 2025-05-05 | REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-VETP-V123-616KM102D | 400000006663 | 6600 | R02 | PM | Low | V123 | 6600 |  |  | 15007167 | 2025-05-05 | 31993840 | 6600RY02
Completed | 170000005262 | 4EM58C2: Fan belt replacement | PM07 | CMC | 3 | 2025-05-06 | WCM REL CSER GMPS MANC PRC SETC |  | HP-REF-6600-FCCU-V010-004EM058C2 | 400000006576 | 6600 | R01 | PM | Low | V010 | 6600 | 004 |  | 15004598 | 2025-05-06 | 31993840 | 6600RY01
Pending | 170000005266 | 8KM106E: Fan belt replacement | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V042-008KM106E | 400000006710 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006209 | 2025-05-09 | 31993840 | 6600RY01
Pending | 170000005267 | 8KM105D: Fan bearings replacement | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V042-008KM105D | 400000006711 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006200 | 2025-05-09 | 31993840 | 6600RY01
Pending | 170000005268 | 8PM104B: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V042-008PM104B | 400000006712 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 12013727 | 2025-05-09 | 31993840 | 6600RY01
Pending | 170000005270 | 42PM22A: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-CRDU-V003-042PM022A | 400000006692 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011674 | 2025-05-09 | 31993840 | 6600RY01
Pending | 170000005271 | 90PM12B: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-DISL-V032-090PM012B | 400000006693 | 6600 | R01 | PM | Low | V032 | 6600 | 090 |  | 12012827 | 2025-05-09 | 31993840 | 6600RY01
Pending | 170000005272 | 616VOCKM101A: Replace Fan bearings | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-VETP-V123-616VOCKM101A | 400000006694 | 6600 | R02 | PM | Low | V123 | 6600 | 616 |  | 15007634 | 2025-05-09 | 31993840 | 6600RY02
Pending | 170000005273 | 606P1801: Inspect Motor DE & Pump DE brg | PM07 | CMC | 3 | 2025-05-09 | CRTD NMAT PRC |  | HP-REF-6600-VCPP-V117 | 400000006695 | 6600 | R02 | PM | Low | 6600 | 6600 |  |  |  | 2025-05-09 | 31993840 | 6600RY02
Pending | 170000005276 | 131PM104A : Motor brgs replacement | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V040-131PM104A | 400000006730 | 6600 | R01 | PM | Low | V040 | 6600 | 131 |  | 12013388 | 2025-05-10 | 31993840 | 6600RY01
Pending | 170000005277 | 130XM010E: Replace Motor bearings | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V040-130XM010E | 400000006731 | 6600 | R01 | PM | Low | V040 | 6600 | 130 |  | 12013355 | 2025-05-10 | 31993840 | 6600RY01
Pending | 170000005282 | 11PM12A: Pump bearings replacement | PM07 | CMC | 3 | 2025-05-13 | WCM EXEC REL CSER GMPS MACM PRC SETC |  | HP-REF-6600-CRDU-V002-011PM012A | 400000006732 | 6600 | R01 | PM | Low | V002 | 6600 | 011 |  | 15003571 | 2025-05-12 | 31993840 | 6600RY01
Pending | 170000005283 | 8KM65A: Motor bearings replacement | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V042-008KM065A | 400000006750 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 12013569 | 2025-05-12 | 31993840 | 6600RY01
Pending | 170000005285 | 170PM7B: Pump DE & NDE brgs replacement | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V029-ROTARYEQPT | 400000006741 | 6600 | R01 | PM | Low | V029 | 6600 | 040 |  |  | 2025-05-13 | 31993840 | 6600RY01
Pending | 170000005286 | 170PM21B: Pump DE bearing replacement | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V029-ROTARYEQPT | 400000006742 | 6600 | R01 | PM | Low | V029 | 6600 | 040 |  |  | 2025-05-13 | 31993840 | 6600RY01
Pending | 170000005287 | 603PM101C: Inspect Coupling shims & repl | PM07 | CMC | 3 | 2025-05-13 | CRTD NMAT PRC |  | HP-REF-6600-VSCT-V114-603PM101C | 400000006743 | 6600 | R02 | PM | Low | V114 | 6600 | 603 |  | 15003372 | 2025-05-13 | 31993840 | 6600RY02
Pending | 170000005293 | 008KM105C: Fan bearings replacement | PM07 | CMC | 3 | 2025-05-14 | CRTD NMAT PRC |  | HP-REF-6600-PNUT-V042-008KM105C | 400000006751 | 6600 | R01 | PM | Low | V042 | 6600 | 008 |  | 15006199 | 2025-05-14 | 31993840 | 6600RY01
Pending | 170000005294 | 092PM009B: Coupling shims inspection | PM07 | CMC | 3 | 2025-05-14 | CRTD NMAT PRC |  | HP-REF-6600-SRUS-V033-092PM009B | 400000006752 | 6600 | R01 | PM | Low | V033 | 6600 | 092 |  | 15006563 | 2025-05-14 | 31993840 | 6600RY01
Pending | 170000005296 | 42M15B: Balancing and run-out checking | PM07 | CMC | 3 | 2025-05-15 | CRTD NMAT PRC |  | HP-REF-6600-CRDU-V003-042PM015B | 400000006780 | 6600 | R01 | PM | Low | V003 | 6600 | 042 |  | 12011660 | 2025-05-15 | 31993840 | 6600RY01